## Project Plan
Master Project Plan
[8 empty] | Sprint 1 — Foundation |  |  |  | Sprint 2 — Integration |  |  |  | Sprint 3 — Production |  |  |  | Sprint 4 — Mobile & CRM |  |  |  | Sprint 5 — Particle.io |  |  |  | Sprint 6 — Unified SSO
| # | Phase / Category | Sprint / Group | Deliverable | Owner | Status | % Done | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
PHASE 1 — SPRINT 1: FOUNDATION & POC ¦ Week 1–4
▸ Edge EMS Runtime — Spykebox TC6 Setup
| 1.1 | P1 · S1 | Edge Device | Edge runtime setup — Debian RT Linux + Docker Engine provisioned on Spykebox TC6 gateway | Dev1 | Planned | 0%
| 1.2 | P1 · S1 | Edge Device | Network segmentation — VLAN isolation for OCPP chargers, Modbus TCP devices and WAN/Cloud uplink | Dev2 | Planned | 0%
| 1.3 | P1 · S1 | Edge Device | Edge container stack — 6 Docker services deployed via docker-compose on gateway | Dev1 | Planned | 0%
| 1.4 | P1 · S1 | Edge Device | EMS runtime container — energy management core service running in production mode | Dev1 | Planned | 0%
| 1.5 | P1 · S1 | Edge Device | Watchdog service — health monitoring, OTA update agent and automatic rollback on failure | Dev1 | Planned | 0%
| 1.6 | P1 · S1 | Edge Device | 4G LTE modem USB dongle — failover WAN path configured | Dev2 | Planned | 0%
| 1.7 | P1 · S1 | Edge Device | Local control loop — sub-100ms response time verified, offline-first autonomous operation | Dev1 | Planned | 0%
▸ Protocol Drivers
| 1.8 | P1 · S1 | Drivers | Modbus TCP/RTU driver — SunSpec baseline for inverter, meter and battery assets | Dev1 | In Progress | 25%
| 1.9 | P1 · S1 | Drivers | OCPP 1.6J EV charger gateway — compatible with KEBA, ABL and Hardy Barth chargers | Dev1 | Planned | 0%
| 1.10 | P1 · S1 | Drivers | DSMR 5.0 smart meter driver — P1 serial port telemetry integration | Dev1 | Planned | 0%
| 1.11 | P1 · S1 | Drivers | Self-consumption controller — real-time symmetric balancing of PV generation vs site load | Dev1 | Planned | 0%
▸ Cloud Infrastructure — Cyso Cloud NL
| 1.12 | P1 · S1 | Cloud Infra | Cloud infrastructure — API and backend servers provisioned on Cyso Cloud Amsterdam | Dev2 | Planned | 0%
| 1.13 | P1 · S1 | Cloud Infra | Time-series database — TimescaleDB provisioned with 150GB storage for telemetry data | Dev2 | Planned | 0%
| 1.14 | P1 · S1 | Cloud Infra | MQTT broker + secure tunnels — VerneMQ message broker with Cloudflare Zero Trust endpoints | Dev2 | Planned | 0%
| 1.15 | P1 · S1 | Cloud Infra | Identity provider — Keycloak SSO configured with dedicated Ecoways tenant realm | Dev2 | Planned | 0%
| 1.16 | P1 · S1 | Cloud Infra | CI/CD pipeline — GitHub Actions workflow with self-hosted build runner | Dev2 | Planned | 0%
▸ Platform Backend — Schema & API Scaffold
| 1.17 | P1 · S1 | Backend | Database schema design — TimescaleDB hypertables, asset registry, telemetry and event models | Dev2 | Planned | 0%
| 1.18 | P1 · S1 | Backend | MQTT topic structure — message contracts for telemetry, commands and device state | Dev2 | Planned | 0%
| 1.19 | P1 · S1 | Backend | Backend API scaffold — REST framework, auth middleware, tenant routing and OpenAPI spec | Dev2 | Planned | 0%
▸ OrbitEMS Web Portal — Basic Monitoring (Sprint 1 deliverable)
| 1.20 | P1 · S1 | Web Portal | OrbitEMS Web Portal — basic monitoring view with live energy flow and device status | Dev3 | Planned | 0%
| 1.21 | P1 · S1 | Web Portal | OrbitEMS Web Portal · Device list — online/warning/offline status indicators per asset | Dev3 | Planned | 0%
| 1.22 | P1 · S1 | Web Portal | OrbitEMS Web Portal · Site overview — real-time PV yield, battery SoC, grid import/export | Dev3 | Planned | 0%
▸ ✓ Acceptance: Pilot site running stable
| ✓1 | P1 · S1 | Milestone | Sprint 1 acceptance — demo + written acceptance report, pilot site live, edge EMS and dashboard verified | Team | Planned |  |  |  |  | ◆
PHASE 1 — SPRINT 2: INTEGRATION & PILOT ¦ Week 5–8
▸ Market Data & Price Integration
| 2.1 | P1 · S2 | Market Data | EPEX SPOT price feed — 15-min day-ahead import with validation and fallback logic | Dev1 | Planned | 0%
| 2.2 | P1 · S2 | Market Data | Day-ahead tariff optimizer — battery charge/discharge schedule based on price signals | Dev1 | Planned | 0%
| 2.3 | P1 · S2 | Market Data | Weather forecast integration — Open-Meteo irradiance API for PV production prediction | Dev1 | Planned | 0%
| 2.4 | P1 · S2 | Market Data | DSO signal integration — ENTSO-E / IEC 60870-5-104 congestion management interface | Dev1 | Planned | 0%
▸ Backend API & Data Layer
▸ Optimization Controllers
| 2.5 | P1 · S2 | Backend API | Optimization API layer — REST endpoints connecting scheduler, peak shaving and curtailment to Web Portal | Dev2 | Planned | 0%
| 2.6 | P1 · S2 | Integration Test | End-to-end integration test — EPEX SPOT → scheduler → battery command → dashboard confirmation | Dev1 | Planned | 0%
| 2.7 | P1 · S2 | Optimization | Peak shaving controller — symmetric/asymmetric/timeslot modes for demand charge reduction | Dev1 | Planned | 0%
| 2.8 | P1 · S2 | Optimization | PV + load forecasting — LSTM neural network predictor with dropout regularisation | Dev1 | Planned | 0%
| 2.9 | P1 · S2 | Optimization | Energy scheduler v2 — evolutionary optimisation engine with 15-min rolling periods | Dev1 | Planned | 0%
| 2.10 | P1 · S2 | Optimization | PV curtailment controller — automatic export reduction during negative price events | Dev1 | Planned | 0%
▸ OrbitEMS Web Portal — Rules Engine & Monitoring
| 2.11 | P1 · S2 | Web Portal | OrbitEMS Web Portal · Rules engine — 6 configurable strategies with schedule, trigger and action | Dev3 | Planned | 0%
| 2.12 | P1 · S2 | Web Portal | OrbitEMS Web Portal · Tariff arbitrage — day-ahead price view, charge schedule and cost forecast | Dev3 | Planned | 0%
| 2.13 | P1 · S2 | Web Portal | OrbitEMS Web Portal · Peak shaving — live demand vs limit monitor with 15-min interval chart | Dev3 | Planned | 0%
| 2.14 | P1 · S2 | UI — Rules Engine | OrbitEMS Web Portal · Grid congestion — event log, load shedding history and DSO signal status | Dev3 | Planned | 0%
▸ ✓ Acceptance: AI optimization live on pilot
| ✓2 | P1 · S2 | Milestone | Sprint 2 acceptance — demo + written acceptance report, EPEX SPOT tariff scheduling + peak shaving verified | Team | Planned | [8 empty] | ◆
PHASE 1 — SPRINT 3: PRODUCTION & ROLL OUT ¦ Week 9–12
▸ Fleet Management Dashboard
| 3.1 | P1 · S3 | Web Portal | OrbitEMS Web Portal · Fleet dashboard — multi-site map view, KPI rollup and status grid | Dev3 | Planned | 0%
| 3.2 | P1 · S3 | Web Portal | OrbitEMS Web Portal · Site detail view — 24h energy history, PV yield, self-consumption % | Dev3 | Planned | 0%
| 3.3 | P1 · S3 | Web Portal | OrbitEMS Web Portal · Fleet KPIs — aggregated PV yield, storage SoC, CO₂ savings and cost delta | Dev3 | Planned | 0%
| 3.4 | P1 · S3 | Deployment | Production rollout — 2–3 additional sites commissioned and onboarded to OrbitEMS platform | Dev1 | Planned | 0%
| 3.5 | P1 · S3 | Web Portal | OrbitEMS Web Portal · Battery management — SoC, SoH, charge/discharge limits and degradation tracking | Dev3 | Planned | 0%
| 3.6 | P1 · S3 | Web Portal | OrbitEMS Web Portal · EV charging — OCPP charger status, smart charge schedule and session history | Dev3 | Planned | 0%
▸ Compliance Logging & Energiewet
| 3.7 | P1 · S3 | Web Portal | OrbitEMS Web Portal · Compliance log — Energiewet regulatory mapping and congestion event history | Dev3 | Planned | 0%
| 3.8 | P1 · S3 | Compliance | Regulator export — grid operator format data export with per-asset CSV and API endpoints | Dev2 | Planned | 0%
| 3.9 | P1 · S3 | Compliance | Audit trail — all user actions logged with filterable audit log and retention policy | Dev2 | Planned | 0%
| 3.10 | P1 · S3 | Compliance | KPI aggregation engine — cost (€), CO₂ (kg), self-consumption (%) and peak demand (kW) metrics | Dev2 | Planned | 0%
| 3.11 | P1 · S3 | API | REST API for Ecoways — external API documentation, API key management and integration access | Dev2 | Planned | 0%
| 3.12 | P1 · S3 | Branding | White-label configuration — Ecoways branding (logo, colours, custom domain) with tenant isolation | Dev3 | Planned | 0%
▸ SLA Monitoring, Testing & Hardening
| 3.13 | P1 · S3 | DevOps | SLA monitoring — Cyso LBaaS health checks, Grafana uptime dashboards | Dev2 | Planned | 0%
| 3.14 | P1 · S3 | DevOps | Alerting — P1/P2/P3 incident response via webhook / email | Dev2 | Planned | 0%
| 3.15 | P1 · S3 | Testing | Hardware-in-the-loop tests — Spykebox + real Modbus devices | Dev1 | Planned | 0%
| 3.16 | P1 · S3 | Testing | Phase 1 acceptance test — all contractual deliverables verified, sign-off test protocol per §7 acceptance terms | Deepak | Planned | 0%
| 3.17 | P1 · S3 | Docs | Documentation & handover pack — SOW checklist, site configs, test results | Deepak | Planned | 0%
| 3.18 | P1 · S3 | DevOps | Production deployment & hardening — TLS, RBAC, image signing, OTA verified | Dev2 | Planned | 0%
▸ ✓ Acceptance: Production-ready, 3 sites live
| ✓3 | P1 · S3 | Milestone | Sprint 3 acceptance — demo + written acceptance report, 3 sites live, compliance and SLA verified | Team | Planned | [12 empty] | ◆
PHASE 2 — SPRINT 4: MOBILE APP & CRM ¦ Week 13–16
▸ End-User Mobile App (React Native)
| 4.1 | P2 · S4 | Mobile App | App shell — React Native, Keycloak SSO auth flow, push notification setup | Dev3 | Planned | 0%
| 4.2 | P2 · S4 | Mobile App | OrbitEMS Mobile App — React Native shell with SSO authentication and push notifications | Dev3 | Planned | 0%
| 4.3 | P2 · S4 | Mobile App | OrbitEMS Mobile App · Energy dashboard — real-time solar, battery, EV and grid flow view | Dev3 | Planned | 0%
| 4.4 | P2 · S4 | Mobile App | OrbitEMS Mobile App · Reports — monthly savings and self-consumption summary for end-users | Dev3 | Planned | 0%
| 4.5 | P2 · S4 | Mobile App | OrbitEMS Mobile App · Alerts — push notifications for price spikes, congestion and SLA events | Dev3 | Planned | 0%
| 4.6 | P2 · S4 | Mobile App | OrbitEMS Mobile App · Site selector — multi-site list with status indicators and quick switch | Dev3 | Planned | 0%
▸ HubSpot CRM — Bidirectional Sync
| 4.7 | P2 · S4 | HubSpot CRM | HubSpot OAuth2 connection — OrbitEOS ↔ HubSpot API setup | Dev2 | Planned | 0%
| 4.8 | P2 · S4 | HubSpot CRM | Bidirectional user sync — contacts push/pull (name, email, role) | Dev2 | Planned | 0%
| 4.9 | P2 · S4 | HubSpot CRM | Bidirectional company sync — accounts ↔ HubSpot companies + site metadata | Dev2 | Planned | 0%
| 4.10 | P2 · S4 | HubSpot CRM | Event webhook — OrbitEOS site events → HubSpot deal/activity log | Dev2 | Planned | 0%
▸ ✓ Acceptance: End-user app live · Real-time energy visibility
| ✓4 | P2 · S4 | Milestone | Mobile app live on App Store + Play Store — CRM pipeline synced | Team | Planned | [16 empty] | ◆
PHASE 2 — SPRINT 5: PARTICLE.IO INTEGRATION ¦ Week 17–20
▸ Particle.io Cloud Integration
| 5.1 | P2 · S5 | Web Portal | OrbitEMS Web Portal · IoT fleet — device list, live telemetry and OTA update status | Dev1 | Planned | 0%
| 5.2 | P2 · S5 | Particle.io | Windmill asset driver — Particle.io → Modbus TCP adapter | Dev1 | Planned | 0%
| 5.3 | P2 · S5 | Particle.io | Multi-protocol adapter — Particle REST+SSE → OrbitEOS entity state | Dev1 | Planned | 0%
| 5.4 | P2 · S5 | Particle.io | IoT device fleet management UI — device list, telemetry, OTA status | Dev3 | Planned | 0%
| 5.5 | P2 · S5 | Particle.io | Intraday EPEX 15-min advanced tariff arbitrage (extension of Sprint 2) | Dev1 | Planned | 0%
▸ ✓ Acceptance: Particle.io live · Windmill telemetry connected
| ✓5 | P2 · S5 | Milestone | Particle.io live — Windmill asset telemetry connected, OTA working | Team | Planned | [20 empty] | ◆
PHASE 2 — SPRINT 6: UNIFIED SSO & LIVE STREAM ¦ Week 21–26
▸ Unified SSO — Sitasys + NXGEN Identity Federation
| 6.1 | P2 · S6 | Unified SSO | Keycloak broker federation — Sitasys IdP + NXGEN IdP linked via OIDC | Dev2 | Planned | 0%
| 6.2 | P2 · S6 | Unified SSO | Sitasys Evalink integration — alarm workflow + OrbitEOS energy event correlation | Dev2 | Planned | 0%
| 6.3 | P2 · S6 | Unified SSO | NXGEN.io cloud — video AI events + OrbitEOS event correlation | Dev2 | Planned | 0%
| 6.4 | P2 · S6 | Unified SSO | Single login — Ecoways · Sitasys · NXGEN portals via federated token | Dev2 | Planned | 0%
| 6.5 | P2 · S6 | Unified SSO | SLA & audit reporting — cross-platform audit trail across all connected systems | Dev2 | Planned | 0%
▸ Live Video Streaming — Edge Camera Relay via Spykebox
| 6.6 | P2 · S6 | Web Portal | OrbitEMS Web Portal · Live video — camera selector with live stream embedded in dashboard | Dev1 | Planned | 0%
| 6.7 | P2 · S6 | Video Streaming | Live stream relay — Spykebox → REST API → OrbitEOS TypeScript adapter | Dev1 | Planned | 0%
| 6.8 | P2 · S6 | Video Streaming | Video stream UI — live view in energy dashboard, camera selector | Dev3 | Planned | 0%
| 6.9 | P2 · S6 | Video Streaming | Alert correlation — NXGEN.io video AI event → OrbitEOS alarm trigger | Dev1 | Planned | 0%
▸ ✓ Acceptance: Unified SSO live · Cross-platform login active
| ✓6 | P2 · S6 | Milestone | Unified SSO live — Sitasys + NXGEN + Ecoways single login · Video stream live | Team | Planned | [26 empty] | ◆
DEVOPS & INFRASTRUCTURE — Continuous across all phases
▸ CI/CD & Deployment Pipeline
| D.1 | DevOps | CI/CD | GitHub Actions — build, test, lint on every PR | Dev2 | In Progress | 25%
| D.2 | DevOps | CI/CD | Docker image build + push to Cyso Object Storage registry | Dev2 | Planned | 0%
| D.3 | DevOps | CI/CD | Staging environment — Cyso s5.medium, mirrors production | Dev2 | Planned | 0%
| D.4 | DevOps | CI/CD | Blue-green OTA deployment to Spykebox edge fleet | Dev2 | Planned | 0%
| D.5 | DevOps | Monitoring | Grafana + Loki — log aggregation, uptime dashboards, alerting | Dev2 | Planned | 0%
| D.6 | DevOps | Monitoring | Redis Sentinel HA — 2× s5.small (session cache + MQTT fanout) | Dev2 | Planned | 0%
| D.7 | DevOps | Security | TLS 1.3 + image signing — TPM-backed keys + Notary v2 verification | Dev2 | Planned | 0%
| D.8 | DevOps | Testing | Vitest unit tests — backend routes, >80% coverage target | Dev2 | In Progress | 25%
| D.9 | DevOps | Testing | Playwright E2E — critical user journeys: site create → device → dashboard | Dev3 | Planned | 0%

## Stakeholder View
Milestone Tracker
| # | Phase | Sprint | Milestone / Acceptance Gate | Target Week | Status | Completion Date | Notes
| M1 | Phase 1 | Sprint 1 | Pilot site live — energy management system operational on first customer site | W4 | Planned
| M2 | Phase 1 | Sprint 2 | Energy optimization active — day-ahead tariff scheduling and peak shaving verified on pilot | W8 | Planned
| M3 | Phase 1 | Sprint 3 | Production rollout complete — 3 sites live with compliance logging and SLA monitoring | W12 | Planned
| M4 | Phase 1 | Sprint 3 | Phase 1 acceptance sign-off — all contractual deliverables verified per acceptance protocol | W12 | Planned
| M5 | Phase 2 | Sprint 4 | Phase 2 kickoff — end-user mobile app (iOS + Android) alpha released | W16 | Planned
| M6 | Phase 2 | Sprint 5 | IoT device integration live — Particle.io cloud + windmill telemetry connected | W20 | Planned
| M7 | Phase 2 | Sprint 6 | Unified single sign-on live — Sitasys, NXGEN and Ecoways portals accessible via one login | W26 | Planned
PROGRESS SUMMARY
| Total Milestones |  |  |  | 7
| Completed |  |  |  | 0
| In Progress |  |  |  | 0
| Remaining |  |  |  | 7